Dartmouth Agricultural Commission

Goal Setting

2002-2003

Farmland Protection

- Mapping, soils and update lots

- Subcommittee:  partner with Dartmouth Agricultural Preservation Trust Fund Council DAPTFC) to prioritize parcels

- 61A application review after October deadline

- New England Small Farm Institute’s “Land Link” Program

- *Recommendations to DAPTFC

Political Action

- Mediation – send notices to Boards 1-2X/year

- Local Right to Farm Law

- Piggery regulations

- Board of Health regulations

- Zoning by-laws

- Attend meetings of other boards

- *Partner with SEMAP

Agricultural Business economic Development

- Grange Community Shared-Use Kitchen

- Labor search

- Support “Buy Local”

- Promote and support UMD courses

- Horse-livestock arena – Town Park, old Fall River Rd., N. Dartmouth

Public Relations/Outreach/Education

- Encourage development of Agricultural Commissions in other towns

- Interaction with other Town boards

- Increase visibility (display in Town Hall)

- Education (liaison and resource library)

- Farm Open House Day

- Newspaper articles

- Circle of friends (lawyer, writer, politically connected, soil scientist, large animal veterinarian, 4-H, grant writer, photographer, web master)

- *Update mailing list

- *Newsletter (include information and deadlines for state and federal funding programs)

* Indicates on-going activities

Westport Agricultural Commission 2003 Goals

Mission:  To facilitate and encourage the pursuit of agriculture in Westport, and

to promote agricultural-based opportunities in town.

| GOAL | TASK | LEADERS | WHEN |
| --- | --- | --- | --- |
| A. Maintain Improved Relations with Town Boards |  |  |  |
|  | 1. Mediate between farmers and state/town boards | Delegated case by case | Ongoing |
|  | 2. Assist/advise Trust Fund and Community Preservation Councils | Karl, John-Jay | Ongoing |
|  | 3. Send a flyer about the work of AgCom to Town Boards 2 x / year |  | 6 and 12/03 |
| B. Public Relations: Advocate for Farmers Issues and Needs |  |  |  |
|  | 1. Develop Public Relations Program | Schmid/Webster | 6/03 agenda |
|  | - Enhance Neighbor relations - Neighbor Dinners - Publish “Living Near a Farm’ | All Tbd Pamphlet Team | Ongoing Tbd 6/03 agenda 8/03 publish |
|  | 3. Formally thank Advisors and friends |  |  |
|  | 4. Get local Right to Farm By-law passed based on existing state law. | Right to Farm Team | 2004 Town Meeting |
|  | 5. Create/update Farm and Forest Map | Anthony/Jeff/ Alyn | 8/03 |
| C. Meet Specific Needs of Farmers |  |  |  |
|  | 1. Find ways of making farming profitable in Westport | All | ongoing |
|  | - Develop local milk processing - Coordinate input & support - Assist in development of business plan - Identify grants | Dairy Team Karl, Jay and JJ Friends/Advisor Grants Team | Fall 2003 Summer 2003 5/03 5-6/03 |
|  | - Develop programs for value-added products - Invite speakers: Barbara Link, Babson College, Irene Winkler - Brainstorm - Have SEMAP presence thru delegate | Trip, Barbara All Charlie | Ongoing By Fall 2003 done |
|  | 4. Survey farmers each year for their input and involvement | Trip | 9/02 agenda fdbk 10/03-draft 11/03-out 12/03-compile-report |

Rehoboth Agricultural Commission 2003-2004 Goals

| GOAL | TASK | MEMERS | WHEN |
| --- | --- | --- | --- |
| A. Operational |  |  |  |
|  | 1. Define mission statement and work plan (FY04) | all | 1/04 |
|  | 2. Define rules of operation – voting, etc. | All | 1/04 |
|  | 3. Determine how to get budget monies from town – visit with Jay Kelly and BOS |  | 2004 Town Meeting |
| B. Public Outreach – Outreach and Media Plan FY 2004 |  |  |  |
|  | - Assemble a flyer about who and what the Ag Com is – for town-wide mailing-visibility and education - develop sound bytes and points to reinforce with media-Rehoboth Reporter, etc. - Consider a regular mailing-quarterly - Develop Ag Com specific mailing list in database format (MsAccess) |  | Spring 2004 |
|  | 2. Visit with all Town Boards and identify a liaison |  | 1/04 |
|  | 3. Work with neighboring AgComs, introduce to SEMAP, Pilgrim RC&D - informal |  | ongoing |
|  | 4. Appoint a Circle of Friends for support and expertise |  | Spring 2004 |
|  | 5. Determine if will have an event in 2004 – get together-fundraiser, etc. Ex: get to know a neighbor day, farm open house day, cable show |  | 1/04 |
| C. Meet Specific Needs of Farmers |  |  |  |
|  | - Determine method to track Rehoboth farmer/ag enterprise needs – public forums, surveys, interviews - review survey work already done - plan for one yearly survey-talk with other AgComs - Implement Plan | All | ongoing |
|  | 2. Advocacy Plan –What Needs to be done |  |  |
| F. Farmland Protection |  |  |  |
|  | 1. Request BOS notify AgCom immediately when property coming out of Chapter 61 |  | ongoing |
|  | 2. Inventory and map all Ch. 61 and lands in farming | Friends | Fall 2004 |
|  | 3. Develop priorities and method for assessing prime farm land i.e., must be saved |  |  |
|  | 4. Create acquisition plan and funding | Friends | Fall 2004 |
| G. Economic Development |  |  |  |
|  | 1. Determine what are immediate needs of farmers-look at agenda items in other AgComs Ex: haypool |  | ongoing |
|  | 2. Identify people and resources to help navigate public monies and resources available to farmers – farm viability monies and smart growth |  | ongoing |
|  | 3. Create match making network/support for farmers to monies and resources |  |  |
|  | 4. Create plan and funding |  |  |

DRAFT

Middleborough Agricultural Commission 2004 Goals

| GOAL | TASK | MEMBERS | WHEN |
| --- | --- | --- | --- |
| A. Proactive Service to the Agricultural Community | 1. Enhance existing relationships with Town Boards 2. Establish relationships with Farmers Markets 3. Promote Middleborough as a “Farm friendly” town 4. Facilitate the Buy Local Campaign in Middleborough and create a model that can be used in other communities. - Establish a presence with MA Ag in the Classroom |  |  |
| B. Long Term Planning | 1. Complete Mapping of agricultural land and assessment of businesses, 61A and protection mechanisms. 2. Explore funding options for farmland protection.. |  |  |
| C. Efficient Commission Operations | 1. Secure ag. Comm. Members and officers 2. Form “Friends” group 3. Maintain representation with SEMAP. 4. Create subcommittees as they are needed. |  |  |